## Guidelines
This file contains three specific planning tools to complete the supplementary information required when submitting a proposal for Readiness Programme support (including for Objetive 3. Aptation planning):
- Budget plan and accompany Budget notes - Procurement and HR plan - Implementation plan
The following considerations are important when completing the budget:
1. Before preparing the Readiness and budget, procurement and HR, and implementation plans, please read the full guidance contained in the Readiness Programme Guidebook, specifically Part IV Sections 5 and 6
2. You can select the appropriate budget categories from the dropdown list in the budget plan:
3. To insert additional rows, right click on the row number below where you wish to insert the new row and choose INSERT.
4. Additional budget categories may be added by manually typing them on the Budget Category sheet:
5. The Budget Notes sheet should be used to record explanations, further details or cost breakdowns for individual lines
Project Management Cost:
Project management costs (PMC) are the direct administrative costs incurred to execute a grant. They should cover only incremental costs incurred due to the GCF contribution. In most cases, these costs are directly related to the support of a dedicated project management unit which manages the day to day execution related activities of the grant.
General Principles for PMC costs:
1. The percentage of PMC financed by GCF should not be more than the percentage share of the overall budget financed by GCF
2. PMC budget thresholds: Up to 7.5 per cent of total activity budget.
> PMC exceeding 7.5 per cent for the readiness (including NAPs) proposals, up to $ 3 million will require detailed documentation
and justification supporting the entire PMC budget.
> The PMC should be shown as a separate component in the project budget. A detailed breakdown of PMC should be provided by budget category.
> Indicative list of eligible project management costs:
> Project staffing and consultants: Project manager, Project Assistant, Procurement personnel, Finance personnel & Support/admin. Personnel
> Other direct costs: Office equipment, Mission related travel cost of the PMU, Project management systems and information technology,
Office supplies, Audit cost
Contingency :
1. Select the appropriate % of Contingency Budget from the dropdown list :
2. Contingency budget for unforeseen costs arising during the grant implementation should not be included in the outcome budget separately.
3. Contingency budget must be used for any unforeseen programme (output level) cost that is unrelated to implementation/service fee.
4. Any use of contingency must be reported to and agreed by the GCF Secretariat in writing in advance provided with justifications that are acceptable to the GCF.
5. If by the end of the grant implementation period, you have not spent Contingency, you may not increase the scope of the project or make any other expenditures using the Contingency.
If you are unsure about how to complete the budget template, please send your query to: countries@gcfund.org
Readiness Grant Budget Preparation Guidelines

## Budget Category
Budget Categories
Audio Visual & Printing
Audit Fee
Consultant - Individual - International
Consultant - Individual - Local
Professional Services – Companies/Firm
IT Equipment
Office Supplies
Travel - International
Travel – Local
Workshop/Training
Indicate additional budget categories
Choose percentage
0
1%
2%
3%

## 6.1 Budget Plan
6.1 Budget Plan
Please add rows for Outcomes, Outputs and Cost Categories as required. Additional budget categories may be added by manually typing them on the Budget Category sheet.
Objectives/Outcomes / Outputs |  |  | Detailed Budget (in US$) | [5 empty] | Total Budget (per outcome) | Expenditure Plan |  |  |  | Executing Entity | Budget notes
|  |  | Budget Categories choose from the drop-down list | Unit | # of Unit | Unit Cost | Total Budget (per budget category) | Total Budget (per sub-outcome) |  | Year 1 | Year 2 | Year 3 | Year 4
Objective 1 : Capacity Building. | Example: Outcome 1.1 Country NDAs or focal points and the network/ systems that enable them to fulfil their roles, responsibilities and policy requirements are operational and effective | Example: Output 1.1.1 NDA operational manual developed and validated | Consultant - Individual - International | W/Day | 30 | 500 | 15000 | 111500 | 111500 |  | 15000 |  |  |  | A
|  |  | Consultant - Individual - Local | W/Day | 30 | 400 | 12000 |  |  | 6000 | 6000 |  |  |  | B
|  |  | Professional Services – Companies/Firm | Lumpsum | 1 | 50000 | 50000 |  |  | 30000 | 20000 |  |  |  | C
|  |  | Workshop/Training | Event | 5 | 5000 | 25000 |  |  | 5000 | 10000 | 10000 |  |  | D
|  |  | Travel – Local | Trip | 15 | 300 | 4500 |  |  |  | 4500
|  |  | Travel - International | Trip | 2 | 2500 | 5000 |  |  |  | 5000
|  | 1.1.2 Output |  |  |  |  | 0 | 0
0
|  | 1.1.3 Output |  |  |  |  | 0 | 0
0
Objective 2 : Strategic Frameworks. | Outcome 2.2 | 2.2.1 Output |  |  |  |  | 0 | 0 | 0
0
|  | 2.2.1 Output |  |  |  |  | 0 | 0
0
Objective # : | Outcome 4.1 | 4.1.1 Output |  |  |  |  | 0 | 0 | 0
0
|  | 4.1.2 Output |  |  |  |  | 0 | 0
0
Total Outcome Budget | [8 empty] | 111500 | 41000 | 60500 | 10000 | 0 | 0
Project Management Cost (PMC) Up to 7.5% of Total Activity Budget |  |  | Consultant - Individual - Local | Month | 5 | 1000 | 5000 | Actual amount and % of PMC requested: | Maximum PMC that can be requested:
|  |  | Audit Fee | Lumpsum | 5 | 500 | 2475
[7 empty] | 0 | do not change the formula | do not change the formula
[7 empty] | 0 | 7475 | 8362.5
[7 empty] | 0 | 6.704% | 7.5%
FOR GREEN CLIMATE FUND SECRETARIAT'S USE ONLY
Breakdown (per budget category) |  |  | Total (per budget category)
Audio Visual & Printing |  |  | 0
Audit Fee |  |  | 2475 |  |  |  | FOR GREEN CLIMATE FUND SECRETARIAT'S USE ONLY
Consultant - Individual - International |  |  | 15000
Consultant - Individual - Local |  |  | 17000 |  |  |  | Total Outcome Budget | [6 empty] | 111500
Professional Services – Companies/Firm |  |  | 50000 |  |  |  | Project Management Cost (PMC) |  | 6.704% | requested |  |  |  | 7475
IT Equipment |  |  | 0 |  |  |  | Contingency | 1% |  | requested |  |  |  | 1115
Office Supplies |  |  | 0
Travel - International |  |  | 5000
Travel – Local |  |  | 4500 |  |  |  | Sub-Total (Total Outcome Budget + Contingency + PMC) | [6 empty] | 120090
Workshop/Training |  |  | 25000
0 |  |  | 0 |  |  |  | Delivery Partner Fee (DP) - Up to 8.5% of the Sub-Total | [6 empty] | 10207.65
0 |  |  | 0
0 |  |  | 0
0 |  |  | 0 |  |  |  | Total Project Budget (Total Activity Budget + Contingency + PMC + DP) | [5 empty] | 130298
0 |  |  | 0
Total Outcome Budget + PMC |  |  | 118975

## Budget Notes
Budget Notes
Please check out the example in the table below, and remove them before including the proposal's entries
Budget Note | Detailed Description
A | Investment specialist (international consultnat) for USD15,000 at USD500/day for 30 days to oversee the investment planning and finance elements notably building investment pipelines and bringing regional and global experience.
B | Local Development Expert (local consultant) for USD12,000 at USD400/day for 30 days expert on local adaptation planning and monitoring and conduct preparatory work and further analysis for activity 3.1.1
C | Professional services - Firm : to engage a firm for USD50,000 lumpsum to implement activity 3.2.1a to conduct a technical diagnostic of 2 coastal sites and recommend solutions for each site.
D | Five one-day workshops for capacity building estimated at USD5,000 per event to include venue and catering for 25 persons (USD200/person) in each coastal community (2 localities).

## Guidlines for Procurement Plan
The following considerations are important when completing the Procurement Plan:
1. Before preparing the Readiness and budget, procurement and HR, and implementation plans, please read the full guidance contained in the Readiness Programme Guidebook, specifically Part IV Sections 5 and 6
2. Please start populating information on planned procurement items next to dedicated rows titled 'Planned'. Utilize slicer buttons at the top of the worksheet to easily filter out rows dedicated to planned items.
3. Please Specify Item and Item Description under Column C.
4. Choose the appropriate Procurement categories from the dropdown list available in the Procurement plan under column D.
5. Specify the Estimated cost of the Item under Column E.
6. Populate the applicable Procurement Method (e.g., open, limited RFP, ITB, RFQ) in Column G. Ensure alignment with the thresholds (Min-Max monetary value for the indicated procurement method) outlined in Column H, in accordance with the applicable procurement policy.
7. In Column I, specify the name of the Entity executing Procurement (DP/EE, etc.).
8. Indicate estimated timelines under Columns J and K.
9. The Procurement Plan Template provides twenty (20) dedicated rows. To insert additional rows, right-click on the row number below where the new row is desired and select INSERT. When inserting new rows, allocate three rows for each item (Planned, Revised1, Actual) and extend existing dropdown menus or other formulas.
10. Utilize Column L, labeled "Remarks," to record explanations, additional details, or any other pertinent information as needed.
The following considerations are important when completing the Change Request impacting the Procurement Plan:
1. Upon approval of the procurement plan by the GCF, the 6.2 Procurement Plan will be locked. Simultaneously, the additional tab 6.2.1 Procurement Plan will be activated for inputs. In this tab, planned items will be automatically populated from the approved procurement plan. Only revisions and actuals can be modified.
2. Change requests within 20% threshold of cost reallocation per procurement category (column D) are not subject to GCF pre-approval provided that the procurement process adheres applicable procurement policy AND follows competitive process.
3. Any change from the approved competitive procurement method to a less competitive method, irrespective of financial value, requires GCF pre-approval. Such changes should be submitted as a change request for clearance.
4. Any change constituting a new procurement item irrespective of financial value requires GCF pre-approval. Such changes should be submitted as a change request for clearance.
5. When revising a procurement item, utilize the designated row labeled "Revised1" and update the relevant columns from the approved procurement plan. After updating, populate Column F with the Current Estimated Cost (latest estimated/actual cost).
6. For subsequent revisions, please add dedicated rows i.e. "Revised2" for the second revision, "Revised3" for the third revision, etc and update Column F on Current Estimated cost accordingly.
7. To add new procurement items outside the approved procurement plan, allocate three rows for each new item (Planned, Revised 1, Actual). Extend existing drop-down menus or other formulas and input information under "Revised 1"
8. For ease of reference please also highlight indicated changes in yellow
9. When deleting procurement items, employ strikethrough and indicate "0" under Column F for the Current Estimated Cost (latest estimated/actual cost).
The following considerations are important when preparing the Annual Progress Report:
1. Please attach this procurement plan to your Annual Progress Report to demonstrate implementation progress as well as any changes that were not sibject to GCF pre-approval as defined in the section above.
The following considerations are important when preparing the Completion Report:
1. Dedicated tab - 6.2.1 Procurement Plan shall illustrate the actual execution of the procurement plan, as a component of the project completion reporting process, in the row titled 'Actual'.
2. Upon provision of actual inputs, the consolidated spreadsheet should delineate information pertaining to the project approval stage. Specifically, the spreadsheet should distinguish between what was initially approved (under the row dedicated to "planned" items), what underwent a single revision (Revised1), what underwent two revisions (Revised2), or remain blank if no revisions occurred. Populate fields related to actual execution, costs, and timelines accordingly.
If you are unsure about how to complete the Procurement Plan template, please send your query to: countries@gcfund.org
Readiness Grant Procurement Plan Preparation Guidelines

## 6.2 Procurement Plan
6.2 Procurement Plan
For goods, services, and consultancies to be procured, please list the items, descriptions in relation to the activities in Section 3, estimated cost, procurement method, relevant threshold, and the estimated dates. Please provide a full procurement plan for the entire duration of the implementation period.
Procurement Plan Approval Date:
Please check out the example in the table below, and remove the items before including the proposal's entries. At the proposal submision stage, please populate the raws dedicated to planned items.
No | Status | Item Description | Category | Estimated Cost (US$) | Current Estimated Cost (please indicate latest estimated/actual cost) | Procurement Method (e.g. open, limited RFP,ITB,RFQ) | Thresholds as per applicable procurement policy (Min-Max monetary value for which indicated procurement method must be used) | Name of Entity executing Procurement (DP/EE, etc.) | Date of initiating procurement (Tender Issuence) | Estimated contract start date | Remarks
1 | Planned | 30 Laptop | Goods | 60000 |  | Open - ITB | 50000-more | DP | 2023-10-26 | 2023-12-26
1 | Revised1
1 | Actual
2 | Planned | 5 Workshop | Non-Consulting Services | 7500 |  | Open- RFQ | 5000-50000 | DP | 2023-10-01 | 2023-11-02 | 5 workshops - $1,500/each
2 | Revised1
2 | Actual
3 | Planned
3 | Revised1
3 | Actual
4 | Planned | M and E Consultant | Consulting Services (Individual Consultants) | 50000 |  | Open - RFP | 5000-50000 | DP | 2023-10-26 | 2023-12-26
4 | Revised1
4 | Actual
5 | Planned
5 | Revised1
5 | Actual
6 | Planned
6 | Revised1
6 | Actual
7 | Planned
7 | Revised1
7 | Actual
8 | Planned
8 | Revised1
8 | Actual
9 | Planned
9 | Revised1
9 | Actual
10 | Planned
10 | Revised1
10 | Actual
11 | Planned
11 | Revised1
11 | Actual
12 | Planned
12 | Revised1
12 | Actual
13 | Planned
13 | Revised1
13 | Actual
14 | Planned
14 | Revised1
14 | Actual
15 | Planned
15 | Revised1
15 | Actual
16 | Planned
16 | Revised1
16 | Actual
17 | Planned
17 | Revised1
17 | Actual
18 | Planned
18 | Revised1
18 | Actual
19 | Planned
19 | Revised1
19 | Actual
20 | Planned
20 | Revised1
20 | Actual
| Planned | Total $(USD) |  | 117500
| Revised1 | Total $(USD) |  | 0
| Actual | Total $(USD) |  | 0
Breakdown per Category
| Planned Goods | Total $(USD) |  | 60000
| Planned Non-Consulting Services | Total $(USD) |  | 7500
| Planned Works | Total $(USD) |  | 0
| Planned Consulting Services (PS) | Total $(USD) |  | 0
| Planned Consulting Services (IC) | Total $(USD) |  | 50000
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## 6.2.1 Procurement Plan Revision
6.2 Procurement Plan
For goods, services, and consultancies to be procured, please list the items, descriptions in relation to the activities in Section 3, estimated cost, procurement method, relevant threshold, and the estimated dates. Please provide a full procurement plan for the entire duration of the implementation period.
Procurement Plan Approval Date:
Please check out the example in the table below, and remove the items before including the proposal's entries. At the proposal submision stage, please populate the raws dedicated to planned items.
No | Status | Item Description | Category | Estimated Cost (US$) | Current Estimated Cost (please indicate latest estimated/actual cost) | Procurement Method (e.g. open, limited RFP,ITB,RFQ) | Thresholds as per applicable procurement policy (Min-Max monetary value for which indicated procurement method must be used) | Name of Entity executing Procurement (DP/EE, etc.) | Date of initiating procurement (Tender Issuence) | Estimated contract start date | Remarks
1 | Planned | 30 Laptop | Goods | 60000 | 0 | Open - ITB | 50000-more | DP | 2023-10-26 | 2023-12-26 | 0
1 | Revised1
1 | Actual | 25 Laptop | Goods | 50000 |  | Open - ITB | 50000-more | DP | 2023-10-26 | 2023-12-26
2 | Planned | 5 Workshop | Non-Consulting Services | 7500 | 0 | Open- RFQ | 5000-50000 | DP | 2023-10-01 | 2023-11-02 | 5 workshops - $1,500/each
2 | Revised1 | 4 Workshop | Non-Consulting Services | 6000 |  | Direct Procurement | N/A | DP | 2023-10-01 | 2023-11-02 | (justification)
2 | Revised2 | 10 Workshop | Non-Consulting Services | 15000 |  | Direct Procurement | N/A | DP | 2023-10-01 | 2023-11-02 | (justification)
2 | Actual
3 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Revised1
3 | Actual
4 | Planned | M and E Consultant | Consulting Services (Individual Consultants) | 50000 | 0 | Open - RFP | 5000-50000 | DP | 2023-10-26 | 2023-12-26 | 0
4 | Revised1
4 | Actual
5 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Revised1
5 | Actual
6 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Revised1
6 | Actual
7 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Revised1
7 | Actual
8 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Revised1
8 | Actual
9 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Revised1
9 | Actual
10 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Revised1
10 | Actual
11 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Revised1
11 | Actual
12 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Revised1
12 | Actual
13 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Revised1
13 | Actual
14 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Revised1
14 | Actual
15 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Revised1
15 | Actual
16 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Revised1
16 | Actual
17 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Revised1
17 | Actual
18 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Revised1
18 | Actual
19 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Revised1
19 | Actual
20 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Revised1
20 | Actual
| Planned | Total $(USD) |  | 117500
| Revised1 | Total $(USD) |  | 6000
| Actual | Total $(USD) |  | 50000
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## 6.3 HR plan
6.3 Human Resources (HR) Plan
For staff to be employed for the duration of the grant.
Please use examples in the table below, and remove them before indicating proposal's requirements.
Item | Item Description | Estimated Cost (US$) | Recruitment Method | Thresholds as per applicaple policy (if any) | Name of Entity executing recruitment (DP/EE, etc.) | Date of initiating recruitment | Estimated contract start date
Example -Project Manager | Full time project manager | 40000 | HR process (open advertisement) | $20,000 - $50,000
Example -Project Accountant | Full time project accountant | 25000 | HR process (Selection from roster) | $20,000 - $50,001
Sub-Total (US$) |  | 65000

## 6.4 Implementation Plan
6.3 Implementation Plan
Column B: Please list all output codes the proposed proposal aims to achieve (e.g., 1.2.1 or 2.1.3., etc.)
Column C: Please indicate the month number in which the output will start the implementation (e.g., month 3 = 3)
Column D: Please indicate the month number in which the output will finish the implementation (e.g., month 9 = 9)
Column E: The duration of the implementation for each output will appear automatically using the formula (C-D); therefore, it is not expected for editing.
Column F: Dependency output(s): If the output listed is depending on other output(s), please list those outputs respectively; otherwise, please type "none"
Please check out the example in the table below, and remove them before including the proposal's entries
Output | Start Date (Month#) | End date (Month#) | Implementation period (Months) | Interdependency output(s)
Example - 1.2.1 | 3 | 6 | 3 | 2.1.2
Example - 1.2.2 | 7 | 12 | 5 | None
Example - 2.1.2 | 3 | 9 | 6 | 1.2.1
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0